TITLE: Lessons Learned Report — Project Closure: Warehouse Management System Rollout

ORGANIZATION: Northwind Analytics, Inc.

DEPARTMENT: PMO

SENSITIVITY: Internal

VERSION: 1.0

EFFECTIVE_DATE: 2026-05-30

_______________________________________________________________________________________________

# Lessons Learned Report — Project Closure: Warehouse Management System Rollout

This report captures lessons learned at the closure of the internal Warehouse Management System (WMS) rollout project, delivered to Northwind Analytics, Inc.' own manufacturing distribution center, completed May 2026.

# 1. Project Outcome

The WMS rollout was delivered 3 weeks later than the original plan and approximately 8% over budget, but achieved its core objectives: reduced pick-error rate from 2.1% to 0.6%, and reduced average order fulfillment time by 22%.

# 2. What Worked Well

Running a 4-week parallel operation (old and new systems side-by-side) before full cutover caught several process gaps without risking live order fulfillment.

Embedding a dedicated "super user" from the warehouse floor in the project team from day one significantly improved floor-level buy-in and reduced training time.

Weekly cross-functional standups (IT, Operations, Warehouse) kept blockers visible and resolved quickly.

# 3. What Could Improve

Initial hardware procurement (handheld scanners) was ordered late because lead time was underestimated by the project team — this was the primary driver of the 3-week delay.

Change management communication to the second and third shifts lagged behind first shift, leading to inconsistent process adoption in early weeks.

The budget did not originally include a contingency line, so the hardware delay's expedited-shipping cost had no buffer to absorb it.

# 4. Recommendations for Future Projects

PMO to require hardware/equipment lead-time confirmation from vendors before baselining any project schedule involving physical equipment procurement.

Standard project budget template to include a minimum 10% contingency line for projects involving hardware or facilities work.

Change management plans to explicitly include a shift-by-shift communication and training schedule for any project affecting 24/7 operations, not just a single "go-live communication."

# 5. Distribution

This report is shared with the PMO lessons-learned repository and referenced in the Project Status Report template's "prior lessons applied" checklist for future warehouse and manufacturing-adjacent IT projects.