TITLE: Post-Implementation Review — Meridian Logistics ERP Rollout

ORGANIZATION: Northwind Analytics, Inc.

DEPARTMENT: IT Services Delivery

SENSITIVITY: Confidential

VERSION: 1.0

EFFECTIVE_DATE: 2026-05-20

_______________________________________________________________________________________________

# Post-Implementation Review — Meridian Logistics ERP Rollout

This Post-Implementation Review (PIR) covers the ERP rollout delivered for client Meridian Logistics (a sample client engagement), a 14-week engagement completed April 2026 by the IT Services delivery team.

# 1. Project Summary

| Metric | Planned | Actual |
| --- | --- | --- |
| Duration | 12 weeks | 14 weeks |
| Budget | $285,000 | $312,000 |
| Go-live defects (Sev 1/2) | < 5 | 8 |
| User adoption at 30 days | 80% | 74% |

# 2. What Went Well

Core finance and procurement modules went live on schedule with no critical defects.

Client stakeholder engagement was strong throughout, with weekly steering committee attendance above 90%.

The data migration dry-run process (introduced mid-project) caught several data quality issues before go-live that would otherwise have caused production defects.

# 3. What Didn't Go Well

Scope for the inventory module expanded significantly after contract signature, driving the 2-week schedule slip and $27,000 budget overrun.

User adoption at 30 days (74%) fell short of the 80% target, concentrated in the warehouse operations user group, who received less hands-on training time than office-based users.

Two Sev-1 defects post-go-live were traced to environment configuration differences between UAT and Production that were not caught during testing.

# 4. Root Causes

The scope expansion stemmed from an incomplete requirements workshop for the inventory module during the sales/pre-sales phase, which did not surface warehouse-specific workflow requirements until deep into delivery. The UAT/Production environment mismatch was traced to a manual environment setup process rather than automated provisioning.

# 5. Recommendations

Delivery to require a dedicated requirements workshop with warehouse/operations stakeholders for any future engagement involving inventory or warehouse modules, before SOW finalization.

Adopt automated environment provisioning (infrastructure-as-code) for UAT/Production parity on all engagements above $200K, starting Q3 2026.

Extend hands-on training allocation for non-office-based user groups by 50% on similar future engagements.

# 6. Sign-off

Reviewed and approved by the Delivery Director and Client Success Manager. Action items assigned above are tracked in the Delivery Excellence backlog with a target close date of end of Q3 2026.